## Start here
The Programme Quality Framework should be used by delivery staff to ensure high quality student social action activities for students, community partners and service users. This is based on the approach used by Student Hubs based on 16 years of delivering structured volunteering in the community, skilled placements with student consultants, incurricular Community Engaged Learning and a wide range of social impact training and events. The exact tasks and timeline will vary activity to activity but this Framework gives an overview of what is required to deliver consistent high quality programmes - you can add the nuance and expertise of your student body and your activity.
To use this framework:
1 | Review the 'Full checklist with notes' to ensure you understand the process. Ensure you have created or reviewed accompanying resources as required.
2 | Remove, edit or add actions in 'Your checklist' as required. This should be based on your knowledge of the activity you are facilitating, and the nuance of the student community you are working with.
3 | Set the deadlines in 'Your checklist' based on your knowledge of the timeline of your activity, and capacity available.
4 | Get started - put in weekly, fortnightly or monthly check in points to review the framework and ensure your high quality delivery is going to plan. Keep notes reflecting any changes made in practice.
5 | Review 'Your checklist' ahead of your next round of delivery to ensure it is fit for purpose and developss alongside your activity to reflect feedback received, best practice and lessons learned.

## Full checklist with notes
Cycle | Partner engagement tasks | Notes | Student leader engagement tasks | Notes | Student participant engagement tasks | Notes
Before activity | Meet in person to finalise delivery plans for the upcoming activity and sign partnership agreement | You may want to discuss an impact framework and collection plan for your activity's community outcomes. Partnership agreement could include: - The expectations in relation to communication - The expectations in relation to delivery logistics - Approaches to policies - Timeline of the agreed partnership - Data protection and sharing agreement | Meet to update student leader and set targets and timeline for the activity | Activity timeline could include: - Application deadline - Training dates - Induction dates - Activity dates - Dates for peer support, social events and reflection sessions | Create and implement activity recruitment plan | Activity recruitment could include: - Social media pages and groups - Newsletters - University emails and portals - Physical flyers and posters - Word of mouth - Stalls
| Collect information relevant for activity accessibility review | Accessibility review could include: - Physical accessibility at venue - Visual accessibility of resources - Availability of toilets, quiet spaces and parking | Share relevant mitigations from activity risk assessment |  | Write activity risk assessment and get necessary sign off
| Collect information relevant for activity risk assessment |  |  |  | Close register your interest form, open application form and update website
Activity recruitment | Send recruitment update | This could include: - Updated expectations on number of students and timeline of activity - A sensecheck on partner engagement - A reminder on activity induction plans | Support to facilitate drop in sessions for students who are interested in the activity |  | Review reasonable adjustment requests
|  |  | Train student leader in how they can support with selection and training |  | Review applications and deliver selection and/or training sessions
|  |  | Start support plan for student leader, to include regular meetings and additional development | Support and benefits could include: - Acces to training activities or social activities - An enhanced reference from the staff team - Access to leader or skill-specific training - Signposting to other leadership opportunities within the university - Accreditation through your university's award scheme | Conduct DBS checks and deliver safeguarding training as required
Organise drop in for final questions and support
[5 empty] | Asign activities, and activity leads, as required | For bigger activities activity leads may support groups of students by: - Checking who has attended each session - Answering questions and liaising with stakeholders where relevant - Creating a supportive and social environment
[5 empty] | Share activity resources/ handbook | Activity resources could include: - Activity and partner details - Travel directions - Communication expectations and key contacts - Accessibility information - Relevant risk mitigations - Information about expenses
During activity | Support to facilitate activity induction | Inductions could include: - Location and travel information - Health and Safety and safeguarding - Specific activity training and information - Expectations (eg signing in, professionalism, communication) - Introduction to key contacts | Support to attend activity induction |  | Invite to attend activity induction
| Have two session check in via phone call | Based on progress of activity decide when to next check in. You could discuss: - A general update - Safeguarding - Concerns and problem solving - Arising threats and opportunities | Support to check in with student participants after each session | If activity leads are in place the student leader can just check in with them, otherwise they should check in with all students on: - Attendance - Number of community members engaged - Concerns | Close application form, open register your interest form and update website
| If partner not present at activity staff attend each session, if partner present staff attend at least once during activity |  | Support to facilitate a social for student participants |  | Contact student participants at least twice throughout activity with a 'newsletter' update | Newletters help to create a sense of community and inform students about social issues. They could include: - An overview of impact - Details on the activity - Information on the social issue being tackled - Signposting to other opportunities to make change
|  |  | Support to facilitate peer support for student participants | Peer support is dedicated time for student to share with and support one another. This could be: - Question based, with prompts from the facilitator - In pairs, to allow more specific time for each individual - Reflection based, guided through a series of questions - Idea sharing, to work through a specific challenge - Action Learning Sets, providing a structured approach to problem solving | Check in with student participants after three sessions (or support student leader to do so) | Three week checkin could include: - Reminder of expectations - Invitation to provide feedback - Check in on wellbeing - Check in on safeguarding
|  |  | Support to celebrate the activity via communications and marketing channels |  | Support drop outs to leave well, including a phone call to check in | You should have clear communication criteria for contacting students who don't attend one, two, and more sessions. Through these communications you could: - Check in on wellbeing - Remind them of expectations - Signpost to other opportunities - Signpost wellbeing support
After activity | Collect feedback and case studies, if relevant from service users as well as partner |  | Support to facilitate a reflection session | Reflection session could include: - Sharing experience of volunteering so far with the group - Reflecting on skills developed, and lessons learned - Reflecting on turning points and feelings - Setting future actions to put learnings into practice and continue personal development | Send end of activity email | Email could include: - Request for feedback - Gauging interest in future engagement - Signposting to other opportunities - Sharing wellbeing support information
| Meet face to face to discuss activity and future plans. Agree soft activity plans for next delivery cycle | Meeting could include: - Feedback on activity - Timeline for future activities - Expectations for future activities | Facilitate reflection session for student leader | Reflection session could include: - Individual reflection on employability and personal development - Group reflection on the success of the activity | Celebrate with a certificate, reference, gift and nominations to Awards as relevant
| Recruit new partners as required, circulating partner pack | Pack could include: - Introduction to you and the activity - Partner expectations - Your approach to sustainability, ED&I, people and culture and safeguarding - Partnership timeline - FAQs Meetings with new partners could include: - Exploring their needs - Discussing hte purpose of the project - Sharing contact details and communication expectations - Setting pross expectations | Send end of activity email | Email could include: - Request for feedback - Gauging interest in future engagement - Signposting to other opportunities - Sharing wellbeing support information | Collect case studies
| Analyse impact, share to celebrate activity, create impact report, and work on activity improvements |  | If student leader not continuing with activity, support to write handover and recruit and induct new student leader as appropriate | Recruitment for new student leaders could include: - Understanding the competencies of the students you are looking for - Assessing student leaders applying for the activity - Communicating the decision and role expectations Induction for new stduent leaders could include: - An introduction to you and the team - An introduction to the activity - Expectations for the role - What they can expect from you | Analyse impact, share to celebrate activity, create impact report, and work on activity improvements
|  |  | Analyse impact, share to celebrate activity, create impact report, and work on activity improvements |  | Reflect on activity, including best practice review, and write up end of activity reflections and learnings

## Your checklist
Cycle | Partner engagement tasks | Deadline | Complete | Student leader engagement tasks | Deadline | Complete | Student participant engagement tasks | Deadline | Complete
Before activity | Meet in person to finalise delivery plans for the upcoming activity and sign partnership agreement |  | FALSE | Meet to update student leader and set targets and timeline for the activity |  | FALSE | Map out activity timeline |  | FALSE
| Collect information relevant for activity accessibility review |  | FALSE | Share relevant mitigations from activity risk assessment |  | FALSE | Create and implement activity recruitment plan |  | FALSE
| Collect information relevant for activity risk assessment |  | FALSE |  |  |  | Write activity risk assessment and get necessary sign off |  | FALSE
[7 empty] | Close register your interest form, open application form and update website |  | FALSE
Activity recruitment | Send recruitment update |  | FALSE | Support to facilitate drop in sessions for students who are interested in the activity |  | FALSE | Review reasonable adjustment requests |  | FALSE
|  |  |  | Train student leader in how they can support with selection and training |  | FALSE | Review applications and deliver selection and/or training sessions |  | FALSE
|  |  |  | Start support plan for student leader, to include regular meetings and additional development |  | FALSE | Conduct DBS checks and deliver safeguarding training as required |  | FALSE
[7 empty] | Organise drop in for final questions and support |  | FALSE
[7 empty] | Asign activities, and activity leads, as required |  | FALSE
[7 empty] | Share project resources to include travel and reimbursement instructions focusing on walking, and cycling routes, and proejct accessibility information |  | FALSE
During activity | Support to facilitate activity induction |  | FALSE | Support to attend activity induction |  | FALSE | Invite to attend activity induction |  | FALSE
| Have two session check in via phone call. Decide whether to sepak again at the end of the activity, or sooner. |  | FALSE | Support to check in with student participants after each session |  | FALSE | Close application form, open register your interest form and update website |  | FALSE
| If partner not present at activity staff attend each session, if partner present staff attend at least once during activity |  | FALSE | Check in weekly with student leader |  | FALSE | Contact student participants at least twice throughout activity with a 'newsletter' update |  | FALSE
|  |  |  | Support to facilitate a social for student participants |  | FALSE | Check in with student participants after three sessions (or support Project Coordinator to do so) |  | FALSE
|  |  |  | Support to facilitate peer support for student participants |  | FALSE | Support drop outs to leave well, including a phone call to check in |  | FALSE
|  |  |  | Support to celebrate the activity via communications and marketing channels |  | FALSE
After activity | Collect feedback and case studies, if relevant from service users as well as partner |  | FALSE | Support to facilitate a reflection session |  | FALSE | Send end of activity email to request feedback, gauge interest in future engagement, signpost to other opportunities and share wellbeing support information |  | FALSE
| Meet face to face to discuss activity and future plans. Agree soft activity plans for next delivery cycle |  | FALSE | Support to collate service user numbers, if relevant |  | FALSE | Celebrate with a certificate, and nominations to Awards as relevant |  | FALSE
| Recruit new partners as require, circulating partner pack |  | FALSE | Facilitate reflection session for project coordinator |  | FALSE | Collect case studies |  | FALSE
| Analyse impact, share to celebrate activity, create impact report, and work on activity improvements |  | FALSE | Send end of activity email to request feedback, gauge interest in future engagement, signpost to other opportunities and share wellbeing support information |  | FALSE | Analyse impact, share to celebrate activity, create impact report, and work on activity improvements |  | FALSE
|  |  |  | If student leader not continuing with activity, support to write handover and recruit and induct new student leader as appropriate |  |  | Reflect on activity, including best practice review, and write up end of activity reflections and learnings |  | FALSE
Analyse impact, share to celebrate activity, create impact report, and work on activity improvements